## Gantt Chart
North Service Pro
PROJECT TITLE |  |  |  | North Services |  |  |  |  | COMPANY NAME | [6 empty] | North Cleaning Services GmbH
PROJECT MANAGER |  |  |  | George Sebastian Cucuiet |  |  |  |  | DATE | [6 empty] | 2025-12-16
WBS NUMBER |  | TASK TITLE | Monthly COST | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE - tools preparation | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[9 empty] | WEEK 31 |  |  |  |  | WEEK 32 |  |  |  |  | WEEK 33 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[9 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 |  | Website
1.1 | SEO |  |  | George | 2025-08-02 | 2025-08-23 | 21 | 0% | bar: WEEK 31 F to WEEK 32 T
1.1.1 |  | Audit |  | George | 2025-08-02 | 2025-08-06 | 4 | 0%
1.1.2 |  | Update WordPress Core & Plugins |  | George | 2025-08-03 | 2025-08-17 | 14 | 0%
1.1.3 |  | Configure Yoast SEO (Free or Premium) |  | George | 2025-08-04 | 2025-08-18 | 14 | 0%
1.1.4 |  | Complete SEO Audit (Technical + On-page) |  | George | 2025-08-05 | 2025-08-19 | 14 | 0%
1.1.5 |  | Keyword Research & Competitor Analysis |  | George | 2025-08-06 | 2025-08-20 | 14 | 0%
1.1.6 |  | On-Page Optimization (Titles, Meta, Alt Text) |  | George | 2025-08-07 | 2025-08-21 | 14 | 0%
1.1.7 |  | Local SEO Setup (Google My Business, Directories) |  | George | 2025-08-08 | 2025-08-22 | 14 | 0%
1.1.8 |  | Backlink Outreach Campaign |  | George | 2025-08-09 | 2025-08-23 | 14 | 0%
1.2 | Email marketing |  |  | George |  |  | 0 | 0%
1.2.1 |  | Define Job Profiles & Requirements |  | George |  |  | 0 | 0%
1.2.2 |  | Publish Job Ads on Platforms |  | George |  |  | 0 | 0%
1.2.3 |  | Screen Applicants |  | George |  |  | 0 | 0%
1.2.4 |  | Conduct Interviews |  | George |  |  | 0 | 0%
1.2.5 |  | Hire & Onboard Staff |  | George |  |  | 0 | 0%
1.3 | Email marketing |  |  | George |  |  | 0 | 0%
1.2.1 |  |  |  | George |  |  | 0 | 0%
1.2.2 |  |  |  | George |  |  | 0 | 0%
1.2.3 |  |  |  | George |  |  | 0 | 0%
1.2.4 |  |  |  | George |  |  | 0 | 0%
1.2.5 |  |  |  | George |  |  | 0 | 0%
2 |  | LLM's
2.1 | Gather Website Requirements & UX Wireframe |  |  | George | 2025-08-07 | 2025-08-08 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Set Up Django Development Environment |  |  | George |  |  | 3 | 0% | bar: WEEK 4 F to WEEK 5 F
2.3 | Develop Core Backend (Models, Admin)
2.4 | Implement Frontend (Templates, CSS, JS) | [5 empty] | 0 | 0%
2.5 | Integrate SEO & API Features
2.6 | Testing & Bug Fixes
2.7 | Launch New Django Website
2.8 |  |  |  | George |  |  | 0 | 0%
3 |  | LLM's
3.1 | OpenAI |  | 29 | George | 2025-08-07 | 2025-08-08 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
3.1 | Claude |  | 20 | George |  |  | 3 | 0% | bar: WEEK 4 F to WEEK 5 F
3.1 | Perplexity |  | 20 | George |  |  | 0 | 0%
3.1 | Cursor AI | [5 empty] | 0 | 0%
4 |  | API's
3.1 | LLM |  |  | George |  |  | 0 | 0%
3.1.1 |  | OpenAI |  | George |  |  | 0 | 0%
3.1.2 |  | Claude |  | George |  |  | 0 | 0%
3.1.3 |  | Perplexity |  | George |  |  | 0 | 0%
3.3 | SEO |  |  | George |  |  | 0 | 0%
3.3.1 |  |  |  | George
3.3.2 |  | SERP |  | George
3.3.3 |  |  |  | George
3.3 | AI Agents |  |  | George |  |  | 0 | 0%
3.3.1 |  | Elevenlabs |  | Malik M |  |  | 0 | 0%
5 |  | Social Media
4.1 |  | Facebook |  | George |  |  | 0 | 10%
4.2 |  | Instagram |  | George |  |  | 0 | 80%
4.3 |  | Linkedin |  | George |  |  | 0 | 0%
4.4 |  | TikTok |  | George |  |  | 0 | 80%
4.5 |  | Canva |  | George |  |  | 0 | 80%
Formulas:
START DATE = MIN([START DATE, row below]:G20)
DUE DATE = MAX([DUE DATE, row below]:H20)
DUE DATE = [START DATE]+[DURATION]

## Task Managemnt
Update WordPress Core & Plugins | SEO | 2025-08-12 | 2 | 2025-08-14
Configure Yoast SEO (Free or Premium) | SEO | 2025-08-14 | 3 | 2025-08-17
Complete SEO Audit (Technical + On-page) | SEO | 2025-08-17 | 5 | 2025-08-22
Keyword Research & Competitor Analysis | SEO | 2025-08-22 | 5 | 2025-08-27
On-Page Optimization (Titles, Meta, Alt Text) | SEO | 2025-08-27 | 7 | 2025-09-03
Local SEO Setup (Google My Business, Directories) | SEO | 2025-09-03 | 5 | 2025-09-08
Backlink Outreach Campaign | SEO | 2025-09-08 | 10 | 2025-09-18
Define Job Profiles & Requirements | Recruitment | 2025-08-12 | 3 | 2025-08-15
Publish Job Ads on Platforms | Recruitment | 2025-08-15 | 4 | 2025-08-19
Screen Applicants | Recruitment | 2025-08-19 | 7 | 2025-08-26
Conduct Interviews | Recruitment | 2025-08-26 | 5 | 2025-08-31
Hire & Onboard Staff | Recruitment | 2025-08-31 | 5 | 2025-09-05
Gather Website Requirements & UX Wireframe | Website Reconstruction | 2025-08-12 | 5 | 2025-08-17
Set Up Django Development Environment | Website Reconstruction | 2025-08-17 | 4 | 2025-08-21
Develop Core Backend (Models, Admin) | Website Reconstruction | 2025-08-21 | 10 | 2025-08-31
Implement Frontend (Templates, CSS, JS) | Website Reconstruction | 2025-08-31 | 8 | 2025-09-08
Integrate SEO & API Features | Website Reconstruction | 2025-09-08 | 7 | 2025-09-15
Testing & Bug Fixes | Website Reconstruction | 2025-09-15 | 5 | 2025-09-20
Launch New Django Website | Website Reconstruction | 2025-09-20 | 2 | 2025-09-22